## Testcase document (hidden)
Pre-requisite
Product functional working documention with expected results/requirements copy should be handed to QA, which will ease the tescase design.
steps to be carried out before going Live - (Pre-Live operations on stage endpoint)
To perform End to End System testing from stage endpoint
To perform Re-testing of logged issues/bug tickets
To perform Regression testing, If all looks good on Re-testing of fixed issues(**Perfoming regression testing is manadate to make sure nothing is breaking and overall flow looks good)
Once E2E system ytesting is completed QA can give Sign-Off
Steps to be carried out after going Live (Post-Live operations on Production endpoint)
To perform quick smoke test on Production endpoint to make sure nothing is breaking and everything looks good on Prod after Go-Live
TC ID | Name of the testcase | Expected results | Actual Results | Status | Tests Executed By | Execution date
Also somwtimes we can follow-
TC ID | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date

## Bug Report (hidden)
Project Name -
Bug / JIRA Ticket ID | Name of the ticket(Title) | Description | Sample TestData | Linked to Parent Ticket/Epic | Related to which fix | Priority | Is it Blocker | Reported By | Assigned To
Priority - | Numbering
High | 1
Medium | 2
Low | 3
sometimes High priority/expedite or blocker isssue is given as priority numbering as 10

## Activesell-DepartmentMTestcases (hidden)
Active sells project portal - stage url: https://hol-activeselling.metro.de/login2
Testing in Chrome browser
Department Manager - Ultra Fresh product
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Home Page
| 1.1 | To validate username and password textfields |  |  | UN: department1_s2_c3_a1@metro-services.in Pwd: metro@123 |  | Looks good | PASS
| 1.2 | To validate "Sign-in" button functionality |  | Click on Sign-in button |  | It should redirect to "Welcome to the Active Selling Assessment !" web page | Looks good | PASS
2 |  | To validate "Welcome to the Active Selling Assessment !" page
| 2.1 | To verify welcome assessment page content |  |  |  | welcome assessment content should be displayed correctly | Looks good | PASS
| 2.2 | To verify Continue button should function correctly |  | Click on Continue button |  | On clicking shoul get redirected to the assesment questionares | Looks good | PASS
3 |  | To validate Assessment Already Submitted page
| 3.1 | To verify PDF assessment form in both the ways: 1. 1. PDF download - on clicking Here 2. Email with pdf |  |  |  | As the assessment already submitted, it should work in 2 ways: 1. PDF download - on clicking Here 2. Email with pdf should be sent to department manager | PDF download looks good email yet to verify | PASS
| 3.2 | To check the functionality of Go back to Homepage button |  | Click on Go back to Homepage button |  | Should redirecty back to homepage | Redirected to home page but content in mentioned on home page is not justified | Low priority but can be fixed | Low priority issue
4 |  | To validate Departmet manager assessment questionares
| 4.1 | To verify Product knowledge level1: Ambassador |  |  |  |  | Some questions show question-mark and some not | There should be unique way | Low priority issue
| 4.2 | Partner
| 4.3 | Champion
| 4.4 | Customer Knowledge level1: Ambassador
| 4.5 | Partner
| 4.6 | Champion
| 4.7 | Sells skills level1: Ambassador
| 4.8 | Partner
| 4.9 | Champion
| 4.11 | To verify Progress bar percentage status |  |  |  |  | looks good for next but if we click on Previous option and check the progress bar percentage it is incorrect | It should show correct percenatage stats | Low priority issue
5 |  | To validate Thank you page
| 5.1 | To validate Thank you page content | [5 empty] | PASS
| 5.2 | To verify functionality of "Go back to homepage" button |  |  |  | It should redirect back to the home page | Looks good | PASS
6 | To validate Profile option web page
| 6.1 | To validate Profile update page |  |  |  |  | In Profile of department manager, phone no address those details are not getting updated and not reflecting when same department manager re-visit the page second time. | It should get reflected in department manager profile | Low priority issue
7 | To validate Home & Logout option web page | [6 empty] | PASS
8 | To validate Support option | [6 empty] | PASS
UltraFresh, Fresh,Wine,Dry food,Non-food and checkin - checkout all types completed in testing

## Activesell-FloorManagerTestcase (hidden)
Active sells project portal - stage url: https://hol-activeselling.metro.de/login2
Testing in Chrome browser
Floor Manager - Ultra Fresh product
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Home Page
| 1.1 | To validate username and password textfields |  |  | UN: department1_s2_c3_a1@metro-services.in Pwd: metro@123 |  | Looks good | PASS
| 1.2 | To validate "Sign-in" button functionality |  | Click on Sign-in button |  | It should redirect to next results web page | Looks good | PASS
2 |  | To validate Assessment Results page
| 2.1 | To verify the stats of department, assessment and validation completed stats |  |  |  | It should show all the stats corectly | Looks good on re-test | PASS
| 2.2 | Changing the icons of stats blocks- that fix is in progress |  |  |  |  | Looks good on re-test | PASS
| 2.3 | To round-off assessment results percentage - in progress with dev |  |  |  |  | Looks good on re-test | PASS
| 2.4 | To validate Assessment Results section |  | Click on Assessment Results block |  | It should redirect to Assessment List web page | Looks good | PASS
3 |  | To validate Assessment List page
| 3.1 | To validate the department wise content and percentage stats |  |  |  | It should reflect the departments and percentage stats correctly |  | PASS
| 3.2 | To verify functioning of Validate button |  |  |  | It should redirect to the Validate info pop-up |  | PASS
| 3.3 | To validate functioning of "View details" button |  |  |  | It should redirecyt to View details's Assessment View page |  | PASS
4 |  | To validate "View details's Assessment View" page
| 4.1 | To validate Department List section |  |  |  | It should show all 6 departments - (Ulta fresh, fresh, wine, dry-food, non-food, checkin-checkout) correctly |  | PASS
| 4.2 | To validate assessment details form with "Edit" button |  |  |  | It should allow to edit the previously made selections |  | PASS
| 4.3 | To validate assessment details form with "Validate" button |  |  |  | Assessment should get validated..no revert allowed |  | PASS
| 4.4 | To validate assessment details form with "Export" button |  |  |  | Export assessment in PDF form |  | PASS
| 4.5 | To validate all detailed percenatge stats of 3 pillars |  |  |  | It should show percentage stats based on selections made |  | PASS
5 |  | To validate Dashboard web page
| 5.1 | To verify percentage stats and graphical represntation |  |  |  |  | Looks good | PASS
6 | To validate Home & Logout option web page | [6 empty] | PASS
7 | To validate Support Page | [6 empty] | PASS
UltraFresh and Fresh food products completed in testing

## Activesell-storemanagertestcase (hidden)
Active sells project portal - stage url: https://hol-activeselling.metro.de/login2
Testing in Chrome browser
store Manager - check-in/checkout
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Home Page
| 1.1 | To validate username and password textfields |  |  |  |  | Looks good | PASS
| 1.2 | To validate "Sign-in" button functionality |  | Click on Sign-in button |  | It should redirect to next results web page | Looks good | PASS
2 |  | To validate Store Report page
| 2.1 | To validate department and other stats content | [5 empty] | PASS
| 2.2 | To validate completion status section | [5 empty] | PASS
| 2.3 | To validate Result section | [5 empty] | PASS
| 2.4 | To validate "View more" button functionality |  | Click on View More button |  | It should allow Edit, Approve and Export functioning correctly |  | PASS
3 | To validate Home & Logout option web page | [6 empty] | PASS
4 | To validate Support Page | [6 empty] | PASS
UltraFresh and Fresh food products completed in testing

## Activesell-countryheadtestcases (hidden)
Active sells project portal - stage url: https://hol-activeselling.metro.de/login2
Testing in Chrome browser
store Manager - check-in/checkout
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Home Page
| 1.1 | To validate username and password textfields |  |  |  |  | Looks good | PASS
| 1.2 | To validate "Sign-in" button functionality |  | Click on Sign-in button |  | It should redirect to next results web page | Looks good | PASS
2 |  | To validate Country head Dashboard | [5 empty] | PASS
3 |  | To validate the functionality of "View Training" |  |  |  |  | Looks good | PASS

## Bug Report-Activesells (hidden)
Active sells bugs
Points to highlight -
1. Some questions formatting is not correct - like in case of some questions question mark is provided and for some it's not provided. We can consider this as future enhancement
2.All paraghph text should be with Justified alignment this gives good look and feel.
3. Progress bar issues for previous button
1
Progess bar shows incorrect percentage stats for "Previous" button click
Current percentage is 22% like below:
On previous button click it shows high percentage in progress bar:
2
Deparment manager UN - department1_s2_c3_a1@metro-services.in
In Profile of department manager, phone no address those details are not getting updated and not reflecting when same department manager re-visit the page second time.
3
Some questions show question mark some not- there should be uniqueness
etc- with'.' and question mark at the end of the question

## SurveyTool-Pakistan-1stDay (hidden)
First day joiner feedback from - http://10.16.148.18/survey-tool-pakistan/pakistan/survey/firstdayfeedback
Testing in Chrome browser
1st Day new joinee survey through Feedback form
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Header part of Feedback form/Survey Form
| 1.1 | To validae main heading of feedback form | [5 empty] | PASS
| 1.2 | To validate sub-heading |  |  |  | It should be New Joiners* | In actual it's New Juniors | FAIL -Can be quick fix
2 |  | To validate Language selection drop down box |  |  |  | Drop down box should show as - Select Language - Urdu * | In actual it shows one of the language name populated | Can be quick fix
3 |  | To validate starting content/text of survey form
|  | To validate the text with alignment, font and look n feel parameters |  |  |  | Suggestion - "your onboarding team" this text should be on below line of "Best Wishes" | in Actual both are on same line | FAIL-Can be quick fix
4 |  | To validate first Rating(0-10) question
| 4.1 | To validate the text - |  |  |  | Absolutely not' and 'Most likely' both should have dot(.) or shouldn't have * | Absolutely not' shows the dot(.)and no dot for 'Most likely' | FAIL-Can be quick fix
| 4.2 | Rating buttions(0-10) functionality |  |  |  | It should show buttion boudries correctly on selection* | lower side button boudry goes off on selection | FAIL-Can be quick fix
5 |  | To validate next questions | [5 empty] | PASS
6 |  | To validate Comment section question1
| 6.1 | To validate question formatting | [5 empty] | PASS
| 6.2 | To validate Answer textfield area |  |  |  | "Your answer" should be in Urdu* | In actual it's shown as "Your answer.." in textfield box * | FAIL-Can be quick fix
7 |  | To validate Comment section question2
| 7.1 | To validate question formatting | [5 empty] | PASS
| 7.2 | To validate Answer textfield area |  |  |  | "Your answer" should be in Urdu* | In actual it's shown as "Your answer.." in textfield box | FAIL-Can be quick fix
8 |  | To validate the functionality of Submit button
| 8.1 | To validate the functoionality of Submit button | [5 empty] | PASS
| 8.2 | To check for Urdu translation of Submit buttion for Pakistan |  |  |  |  | In actual it's in English language which is incorrect. | FAIL- can be quick fix
8 | To validate automated emails sent to new joiner - email on 1st day and 3rd month email
9 | To validate email sent to line manager on 3rd month
Query - To ask in stand-up do we get email notification on succesful submission of feedback forms or it's something different
On first day of On-boarding process, candidate or new jioner will get automated email to fill up the survey with link of Survey portal provided there.
Forms working modules
On submission this page comes up
Translated to english from urdu

## Profitibilty-Bug Report
Project Name - Metro Slovakia Profitability tool project
Project URL - http://10.16.148.79/profitability-tool/public/
NNBP page - http://10.16.148.79/profitability-tool/public/nnnbp_screen
Credentials - My IDAM credentials
NOT FOR TESTING
TC ID | Sub-TC number | Name of the testcase | Expected Results | Actual Results | Status | Suggestions/Comments | Confirmed with dev | Developer Fixes
1 |  | To validate Log - In Page
| 1.1 | To validae main heading of Log-in page | It should show correctly | In actual it's Left aligned | Bug | Heading should be centrally aligned | Already pre-defined
| 1.2 | To validate sub-heading | It should be shown correctly | Looks Good | PASS
| 1.3 | To validate Username | It should be shown correctly | Looks Good | PASS
| 1.4 | To validate Password | It should be shown correctly | Looks Good | PASS | For password threshold of alpha-numerice combination should be provided below -like 8 character password needed and so on..
| 1.5 | To validate Footer part | It should show 2022 year | It shows 2021 year | Bug | What is expected 2022 or 2020/ 2021?, because some pages show as 2022 and some as 2021 and this as 2020
| 1.6 | To validate the functionality of Log-in button | It should work correctly | Looks Good | PASS
2 |  | To validate Home Page/Customer Page
| 2.1 | To validate the Heading and text with alignment, font and look n feel parameters | It should be "Metro Business Soluntion center" or releaveant to that | In actual it shows as "Metro Services" | Bug |  | Dev will confirm with business | PENDING
| 2.2 | To validate "Customer HO Number" filed | Ideally the attribute name/heading should be "Customer HO Number" | In actual It shows "Customer ico" | Bug | Not allowing to type the number in textbox Suggestion - To confirm once with dev what is expected | Not an issue | Not an issue - ico no. is more preferable as per docs. ( Also There is search box to enter ico no.)
| 2.3 | To validate "Linked Customer No." field | It should work correctly and allow multi selections | Looks Good | PASS
| 2.4 | To validate "Article Category" | It should work correctly and allow multi selections | In actual it's not allowing to select multiple article categories | Bug | - Not allowing to select multiple article categories at the same time Apart from above other functionality look fine | Dev will confirm with business | NOT Rquired
| 2.5 | To validate "channel type" filed | It should work correctly and show all possible options | Looks Good | PASS
| 2.6 | To validate "From and To date" filed of Calender | It should work correctly and show all possible options | In actual calender is not shown correctly. It shows only 2020-2022 | Bug | Not showing all years correctly - is it expected? | Dev will confirm with business | Not an issue, As per data available in the DB we have shown only that years on frontend
| 2.7 | To validate Month id filed | It should show month from the calender correctly | In actual it shows only Jan-Feb months and other months | Bug |  |  | DONE
| 2.8 | To validate Quarter field | It should show all 4 quarters correctly | Looks Good | PASS
| 2.9 | To validate functionality of "Show Data" button | It should work correctly and show the expected data | Looks Good | Bug | Suggestion - When we click on Show data, the quarter shows 2 quarter names and then goes off. Also all selected information goes off. Ideallly it should remain as it in upper section | Bug - confirmed with dev | DONE
| 2.11 | To validate "Category Sales Share" column of "Sales Share" table | It should show the expected data correctly | Looks Good | PASS
| 2.12 | To validate "Sales Share%" column of "Sales Share" table | It should show the expected data correctly and percentage total should be always 100 | In actual column name/heading is missing in the table | Bug | Is it expected? Suggestion - Ideally it should have column name as "Sales share%" |  | DONE
| 2.13 | To validate "Sales history and Trends" table | It should show the expected data correctly | In actual column name/heading is missing for first column in the table | Bug | Is it expected? Suggestion - Ideally it should have column name as "Quarter Detail" or something like relevant 2. Also Last 9 Month is missing in the quarter column-is it expected? As we show 4 quarters it should be there | Dev will confirm with DB manager | PENDING
| 2.14 | To validate Article details entries table
| 2.14.1 | To validate show entries drop down box | It should work correctly | Looks Good | PASS | Suggestion- entry tanble size dimensions should be same as upper tables sizes
| 2.14.2 | To validate search box functionality | It should work correctly | Looks Good | PASS
| 2.14.3 | To validate table columns heading | It show be arranged and aligned in correct way | Looks Good | PASS
| 2.14.4 | To validate article entries/data from table | It should be shown correctly | Looks Good | PASS | Can we show all columns in a single glance - to confirm with dev
| 2.14.5 | To validate the selection of article entries | It should be selected correctly | Looks Good | PASS
| 2.14.6 | To validate the "Go To Offer List" button | It should re-direct to the offer logic calculation page | Looks Good | PASS
| 2.14.7 | To validate the footer of article entries table | Heading names not needed | It shows same column heading names in the footer as well. Not required else align it correctly | Bug | We can remove those names from footer Heading names can be aligned correctly in sync with data |  | DONE
| 2.15 | To validate Footer part of Customer page | It should be shown correctly | Looks Good | PASS
| 2.16 | Customer Page Menu list | It should be shown correctly and show all menus of the project | In actual on left hand side menu list shows only "Customer" label, nnbp and *other labels are not shown there | Bug |  |  | NOT an issue nnnbp menu is only for 2 users => martin and matej (not for all of us)
3 |  | To validate Offers- list Page
| 3.1 | To validate "Show"number of entries drop down | It should be shown correctly | Looks Good | PASS
| 3.2 | To validate search box functionality | It should work correctly | Looks Good | PASS
| 3.3 | To validate column headings | It should be shown correctly | Looks Good | PASS
| 3.4 | To validate selected article entries data from table | It should be shown correctly | in actual article data is not lined up exactly below the column headings…it's somewhat ahead of heading | Bug |  |  | DONE
| 3.5 | To validytae input fileds of Colli and prices | It should be shown correctly | In actual it's not showing input boxes correctly | Bug |  |  | DONE
| 3.6 | To validate BackBonus calculation | It should calculate and show the value of Back bonus calculation | On clicking the button calculate backbonus it's not giving the result of calculation | Bug | Alert should get displayed when we select same type |  | DONE
| 3.6.1 | To validate ICO no, Unique no and Quarters fields | It should fetch the same value of those fields from previous page | Looks Good | PASS
| 3.6.2 | To validate the type BULK field | It should be shown correctly | Looks Good | Bug | Suggestion - to mention "Select word" instaed of listing same Bulk bonus type in the drop-down list | Confirmed with dev - Bug | DONE
| 3.6.3 | To validate Spirits field | It should be shown correctly | Looks Good | PASS
| 3.6.4 | To validate Regular field | It should be shown correctly | Looks Good | PASS
| 3.6.5 | To validate Promo field | It should be shown correctly | Looks Good | PASS
| 3.6.6 | To validate CIP field | It should be shown correctly | Looks Good | PASS
| 3.6.7 | To validate Type1 filed | It should be shown correctly | Looks Good | PASS
| 3.6.8 | To validate Add level button | It should be shown correctly | Looks Good | PASS
| 3.6.9 | To validate Calculate Back bonus button | It should show all calculated values correctly | Looks Good | PASS
| 3.6.10 | To validate Calculate OTI button | It should show calculated OTI correctly in Forecast OTI% | Looks Good | PASS
| 3.7 | To validate Forecasted OTI % | It should show all calculated values correctly | Looks Good | PASS | Suggestion -OTI% will be shown in upper box as a part of user-friendly
| 3.8 | To validate footer of Offer List Page | It should be shown correctly | Looks Good | PASS
| 3.9 | To validate warning messages/error messages on Offerlist page | It should be shown correctly | In actual it should throw warning if we don't fill up Type1/ add to calculate Back-bonus | Bug | Suggestion - one random error message just blinking in some selection, can we display it correctly as a fixed one so that user can read that error |  | DONE
| 3.1.0 | To validate BackBonus calculation for same bonus type | It should show all calculated values correctly | In actual evey time it gives Back Bonus value as '0' which is incorrect | Bug |  |  | DONE
| 3.11 | To validate Back-bonus value for more than one linked customer | It should show all calculated values correctly | In actual evey time it gives Back Bonus value as '0' which is incorrect | Bug |  |  | DONE
4 |  | To validate NNBP update module
| 4.1 | To validate the header of NNBP page | It should be shown correctly | Looks Good | PASS
| 4.2 | To validate Home redirect icon | It should work correctly | Looks Good | PASS
| 4.3 | To validate Show entries drop down box | It should work correctly | Looks Good | PASS
| 4.4 | To validate Search box functionality | It should work correctly | Looks Good | PASS
| 4.5 | To validate table column headings | It should be shown correctly | Looks Good | PASS
| 4.5 | To validate NNBP table entries with toggle button functionality | It should be shown correctly | Looks Good | PASS
| 4.5.1 | To validate some toggle function for specific entries | It should be shown correctly | In actual Alert box pop-up comes multiple times. It should come only once | Bug |  |  | DONE
| 4.6 | To validate the footer part of NNBP table | It should be shown correctly | In actual same column heading names are repated at footer as well, not required | Bug | Heading names can be aligned but not high priority issue |  | DONE
| 4.7 | To validate the footer section of NNBP page | It should be shown correctly | Looks Good | PASS
5 |  | To validate Profile page
| 5.1 | To validate Profile textfilelds | Data should be added correctly- Profile page should update | In actual Data like Phone no, Address is not getting updated | Bug
| 5.2 | To validate Update Button | It should work correcctly and update the page with alert message | In actual Update button fails with error page whenever profile image uploaded for profile page | Bug
6 |  | To validate Log-out page
| 6.1 | To validate Log-out | It should function correctly | In actual it shows name as Metro Service instead of "Metro Business solution center" | Bug | Dev Confirm with Business
| 6.2 | To validate Log-in button from Log-out page | It should allow to log-in back | Looks good | PASS
7 |  | To validate Forgot Password page
| 7.1 | To validate all textfilelds to re-set password | It should show all textfilelds correctly | Looks good | PASS
| 7.2 | To validate Cancel button | It should cancel the process and go back to Log-in page | In actual Cancel button is not working correctly and not going back to login page on clicking cancel button | Bug
| 7.3 | To validate footer part of Forgot password page | It should show footer correctly | It shows year as 2020 | Bug | What is expected 2022 or 2020/ 2021?, because some pages show as 2022 and some as 2021 and this as 2020
Back-Bonus Calulation:
Backbonus = Limit base * Selected bonus % (Selected bonus value is the percentage value that we enter in Type1/2)
Limit base = every value including Limit word is considered from Bulk,spirits,Regular, promo, CIP data tables
Bonus Base = "Limit and Bonus" values are considered in Bonus base value
Historical OTI = OTI% from data table
Forecasted OTI : It gives in future - how much discount will be offered

## ConfirmationFromClient (hidden)
Below are some checkpoints which needs to confrim from Client once.
TC ID | Sub-TC number | Name of the testcase | Expected Results | Actual Results | Status | 1st Day New Joiner | 3rd Month New Joiner | 3rd MonthLM
1 |  | To validate Header part of Feedback form/Survey Form
| 1.2 | To validate sub-heading | It should be New Joiners* | In actual it's New Juniors | To confirm with Client FAIL - Can be quick fix | Bug Retesting - still not fixed - Waiting for reponse from client because we got Urdu translation like Junior | Suggestion - It can be - New Joiners Third Month On Boarding Survey - Dev will confirm with Customer | Suggestion - It can be - Line Manager's Third Month On-Boarding Survey - Dev will confirm with Customer
3 |  | To validate starting content/text of survey form
| 3.1 | To validate the text with alignment, font and look n feel parameters | Suggestion - "your onboarding team" this text should be on below line of "Best Wishes"* | in Actual both are on same line which doesn't look good | To confirm with Client FAIL - Can be quick fix | Bug Re-testing - Keeping on same line for now so looks good ** to confirm once | Bug Re-testing - Keeping on same line for now so looks good ** to confirm once | Bug Re-testing - FAIL, It's not arranged correctly something wrong **Need to confirm with client
4 |  | To validate first Rating(0-10) question
| 4.1 | To validate the text - | Absolutely not' and 'Most likely' both should have dot(.) or shouldn't have * | Absolutely not' shows the dot(.)and no dot for 'Most likely' | To confirm with Client FAIL-Can be quick fix | Bug Retesting - still not fixed - It's due to Urdu language ** to confirm once | Bug Retesting - still not fixed - It's due to Urdu language | Bug Retesting - still not fixed - It's due to Urdu language
5 | 5.1 | To validate the additional store experience question | First radio button option should be" Yes" and third radio button option should be "I am not a store employee" | In actual it shows first option as "Here" and third option as "I am a store employee" | To confirm with Client | NA | Specifc to 3rd month new joiner form and dashboard as dashboard shows it as "I am not a store employee" | NA
6 | 6.1 | To validate next questions with radio button options | It should show questions correctly* | 3rd month LM bug - Bug - It shows "To Disagree" option instead of "Disagreement" | To confirm with Client Quick fix | Pass | Bug Re-testing: Looks good now | Bug - It shows "To Disagree" option instead of "Disagreement" Re-testing - FAIL still not fixed
Dashboard Bug Report
TC ID | Sub-TC number | Name of the testcase | Expected Results | Actual Results | Status | 1st Day New Joiner | 3rd Month New Joiner | 3rd MonthLM
11 |  | To validate entry table
| 11.1 | To validate excel file download functionality | Suggestion -Confirm with dev - what comes in Negative Experiences.It can be remaned as "Suggestions"* | In actual it shows those suggestion comments as Negative experience | Dev will confirm with Business | Dev will confirm with Business | Dev will confirm with Business | Dev will confirm with Business
| 11.4 | To test the functionality of "Previous" button | It should redirect to the previous page and aligned at Left side or have spacing between previous and next* | In actual spacing is not upto the mark | To confirm with Client FAIL - Can be Quick fix | Bug Re-testing : Yet no spacing between previous and next | Bug Re-testing : Yet no spacing between previous and next | Bug Re-testing : Yet no spacing between previous and next
| 11.5 | To test the functionality of "Next" button | It should redirect to the next page and aligned at Right side or have spacing between previous and next* | In actual spacing is not upto the mark | To confirm with Client FAIL - Can be Quick fix | Bug Re-testing : Yet no spacing between previous and next | Bug Re-testing : Yet no spacing between previous and next | Bug Re-testing : Yet no spacing between previous and next
Snaps of store employee checkpoint 5
Dashboard snap of 3rd month new joiner
3rd month new joiner:

## SurveyTool-Pakistan-3rdMonth (hidden)
3rd Month joiner feedback form - http://10.16.148.18/survey-tool-pakistan/pakistan/survey/thirdmonthfeedback
Testing in Chrome browser
3rd Month new joinee survey through Feedback form
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Header part of Feedback form/Survey Form
| 1.1 | To validae main heading of feedback form | [5 empty] | PASS
| 1.2 | To validate sub-heading |  |  |  | Suggestion - It can be - New Joiners Third Month On Boarding Survey | Metro New Joiners Third Month Survey - On Boarding | Can be quick fix
2 |  | To validate Language selection drop-down box |  |  |  | No language selection drop down box added in survey form* | No language selection drop down box added in survey form | Can be quick fix
3 |  | To validate starting content/text of survey form
| 3.1 | To validate the text with alignment, font and look n feel parameters |  |  |  | Suggestion - "your onboarding team" this text should be on below line of "Best Wishes" | in Actual both are on same line | FAIL-Can be quick fix
| 3.2 | To validate Content body/Text |  |  |  | "On boarding" should be only once appeared in the sentence * | in Actual showing it 2 times in the body part | FAIL-Can be quick fix
4 |  | To validate first Rating(0-10) question
| 4.1 | To validate the text - |  |  |  | Absolutely not' and 'Most likely' both should have dot(.) or shouldn't have* | Absolutely not' shows the dot(.)and no dot for 'Most likely' | FAIL-Can be quick fix
| 4.2 | Rating buttions(0-10) functionality |  |  |  | It should show buttion boudries correctly on selection* | lower side button boudry goes off on selection | FAIL-Can be quick fix
4 |  | To validate next questions
| 4.1 | To validate next downward 5 questions |  |  |  | It should show questions correctly* | Additional letter 'e' shown in next 5 questions | FAIL-Can be quick fix
5 |  | To validate Comment section question1
| 5.1 | To validate question formatting |  |  |  | Question should be shown correctly* | Question is not appearing in Urdu language | FAIL-Can be quick fix
| 5.2 | To validate Answer textfield area |  |  |  | Your answer should be in Urdu* | In actual it's shown as "Your answer.." in textfield box | FAIL-Can be quick fix
6 |  | To validate Comment section question2
| 6.1 | To validate question formatting |  |  |  | Question should be shown correctly* | Question is not appearing in Urdu language | FAIL-Can be quick fix
| 6.2 | To validate Answer textfield area |  |  |  | Your answer should be in Urdu* | In actual it's shown as "Your answer.." in textfield box | FAIL-Can be quick fix
8 |  | To validate the functionality of Submit button |  |  |  | It should be clicked correctly and redirect to the form submitted page | Looks Good | PASS
Urdu*
8 | To validate automated emails sent to new joiner - email on 1st day and 3rd month email
9 | To validate email sent to line manager on 3rd month
Forms working modules
On submission this page comes up
Translated to english from urdu

## SurveyTool-Pakistan-3rdManager (hidden)
3rd Month Line manger feedback form - http://10.16.148.18/survey-tool-pakistan/pakistan/survey/thirdmonthfeedbacklm
Testing in Chrome browser
3rd Month Line Manager survey through Feedback form
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Header part of Feedback form/Survey Form
| 1.1 | To validae main heading of feedback form | [5 empty] | PASS
| 1.2 | To validate sub-heading |  |  |  | Suggestion - It can be - Line Manager's Third Month On-Boarding Survey | In actual it is - Metro Line Manager Third Month Survey - On Boarding | Can be quick fix
2 |  | To validate Language selection drop down box |  |  |  | Drop down box should show as - Select Language in Urdu * | In actual it shows one of the language name populated | Can be quick fix
3 |  | To validate starting content/text of survey form
| 3.1 | To validate the text with alignment, font and look n feel parameters |  |  |  | Suggestion - "your onboarding team" this text should be on below line of "Best Wishes"* | in Actual both are on same line to fix by dev for next line/same line | FAIL-Can be quick fix
| 3.2 | To validate Content body/Text |  |  |  |  | You or We what should be there in "You can now" | Dev confirming
4 |  | To validate select employee drop down box |  |  |  | It not in Urdu* |  | FAIL-Can be quick fix
| 4.1 | To validate select employee drop down box |  |  |  | It should be translated in Urdu | Not translated in Urdu. Not seeing any list of employees to me - confirm with dev | FAIL-Can be quick fix
5 |  | To validate first Rating(0-10) question
| 5.1 | To validate the text - |  |  |  | Absolutely not' and 'Most likely' both should have dot(.) or shouldn't have* | Absolutely not' shows the dot(.)and no dot for 'Most likely' | FAIL-Can be quick fix
| 5.2 | Rating buttions(0-10) functionality |  |  |  | It should show buttion boudries correctly on selection* | lower side button boudry goes off on selection | FAIL-Can be quick fix
6 |  | To valoidate next 3 questions with Radio button option
| 6.1 | To validate next downward 3 questions |  |  |  | It should show questions and options correctly* | 3rd option for each question is "To disagree". It should be "Disagreement" as like other 2 forms | FAIL-Can be quick fix
7 |  | To validate Comment section question1
| 7.1 | To validate question formatting |  |  |  | Question should be shown correctly |  | PASS
| 7.2 | To validate Answer textfield area |  |  |  | Your answer from textfield box should be in Urdu | In actual it's shown as "Your answer.." in textfield box | FAIL-Can be quick fix
8 |  | To validate Comment section question2
| 8.1 | To validate question formatting |  |  |  | Question should be shown correctly |  | PASS
| 8.2 | To validate Answer textfield area |  |  |  | Your answer from textfield box should be in Urdu | In actual it's shown as "Your answer.." in textfield box | FAIL-Can be quick fix
8 |  | To validate the functionality of Submit button |  |  |  | It should be clicked correctly and redirect to the form submitted page | Looks Good | PASS
Urdu*
8 | To validate automated emails sent to new joiner - email on 1st day and 3rd month email
9 | To validate email sent to line manager on 3rd month
Forms working modules
On submission this page comes up
Translated to english from urdu

## SurveyTool-Pak-Dashboard1Day (hidden)
Dashboard url -http://10.16.148.18/survey-tool-pakistan/pakistan/survey/dashboard
Testing in Chrome browser
1st Day New Joiner Dashoboard functionality
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Header part of Feedback Dashboard |  |  |  |  | Can be center aligned - confirm with dev
2 |  | To validate 1st day new joiner KPI dashboard
| 2.1 | To check the functionality of "1st day new joiner" button |  |  |  | It should show KPI data of 1st day new joiner | Looks Good | PASS
| 2.2 | To validate Date selection field
| 2.3 | To validate "Select Country" drop down box |  |  |  | It should show country options to select in drop down box | Country options are not shown in drop-down box |  | To check on Post-Live
| 2.4 | To validate "Select City" drop down box |  |  |  | It should show city options to select in drop down box | City options are not shown in drop-down box
| 2.5 | To validate "Select Company" drop down box |  |  |  | It should show company options to select in drop down box | Company options are not shown in drop-down box
| 2.6 | To validate "Select department unit" drop down box |  |  |  | It should show department options to select in drop down box | Department options are not shown in drop-down box
3 |  | To validate "Total no. of people filled the form"
| 3.1 | To validate the title formatting | [5 empty] | PASS
| 3.2 | To validate the count | [5 empty] | PASS
4 |  | To validate "Avarage overall onboarding experience"
| 4.1 | To validate the title formatting |  |  |  | As a suggestion-It's fine ni bug - It can be - "Avearge no. of Overall Onboarding experience", also to ask about ":" should be shown after name or not* | In actual it is - "Average Overall Onboarding Experience" | To confirm with dev - removing colon
| 4.2 | To validate the count |  |  |  | As a suggestion- It should be round off instaed of in decimal like 8/10 instaed of 8.25/10 - Discussed no need to change | In actaul it shows decimal point value - 8.25/10 | PASS no need to change
5 |  | To validate NPS section |  |  |  | To check once with dev for all options working |  | PASS
6 |  | To valiate Detractor, passive and promoters section |  |  |  | To check once with dev for all options working and also do we need to show colon or not* |  | Options will be shown - not an issue
7 |  | To validate Key Performance indicator | [5 empty] | PASS
8 |  | To validate qudrant chart | [5 empty] | PASS
9 |  | To validate employees faviourites word cloud | [5 empty] | PASS
10 |  | To validate Suggestions and Recommendations Word Cloud | [5 empty] | PASS
11 |  | To validate entry table
| 11.1 | To validate excel file download functionality |  |  |  | Suggestion -Confirm with dev - what comes in Negative Experiences.It can be remaned as "Suggestions"* |  | PASS
| 11.2 | To validate Search box functionality | [5 empty] | PASS
| 11.3 | To validate table entries formatting - Positive experience |  |  |  | Even the large text should be accomadataed withing the table margins* | Large text sentence are going out of the margin boundries | FAIL - Can be Quick fix
| 11.4 | To test the functionality of "Previous" button |  |  |  | It should redirect to the previous page and aligned at Left side* | In actual it's not redirecting to the next web page | FAIL - Can be Quick fix
| 11.5 | To test the functionality of "Next" button |  |  |  | It should redirect to the next page and aligned at Right side* | In actual it's not redirecting to the next web page | FAIL - Can be Quick fix
8 | To validate automated emails sent to new joiner - email on 1st day and 3rd month email
9 | To validate email sent to line manager on 3rd month
Forms working modules
On submission this page comes up
Translated to english from urdu

## SurveyTool-Dashboard3rdM-joinee (hidden)
Dashboard url -http://10.16.148.18/survey-tool-pakistan/pakistan/survey/dashboard
Testing in Chrome browser
3rd Month New Joiner Dashoboard functionality
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Header part of Feedback Dashboard |  |  |  |  | Can be center aligned - confirm with dev
2 |  | To validate 3rd Month new joiner KPI dashboard
| 2.1 | To check the functionality of "3rd Month new joiner" button |  |  |  | It should show KPI data of 3rd Month new joiner | Looks Good | PASS
| 2.2 | To validate Date selection field
| 2.3 | To validate "Select Country" drop down box |  |  |  | It should show country options to select in drop down box | Country options are not shown in drop-down box |  | Post live checkpoint
| 2.4 | To validate "Select City" drop down box |  |  |  | It should show city options to select in drop down box | City options are not shown in drop-down box
| 2.5 | To validate "Select Company" drop down box |  |  |  | It should show company options to select in drop down box | Company options are not shown in drop-down box
| 2.6 | To validate "Select department unit" drop down box |  |  |  | It should show department options to select in drop down box | Department options are not shown in drop-down box
3 |  | To validate "Total no. of people filled the form"
| 3.1 | To validate the title formatting | [5 empty] | PASS
| 3.2 | To validate the count | [5 empty] | PASS
4 |  | To validate "Avarage overall onboarding experience"
| 4.1 | To validate the title formatting |  |  |  | As a suggestion- It can be - "Avearge no. of Overall Onboarding experience", also to ask about ":" should be shown after name or not* | In actual it is - "Average Overall Onboarding Experience" | To confirm with dev
| 4.2 | To validate the count |  |  |  | As a suggestion- It should be round off instaed of in decimal like 8/10 instaed of 8.25/10 - No need to change | In actaul it shows decimal point value - 8.25/10 | To confirm with dev
5 |  | To validate NPS section |  |  |  | To check once with dev for all options working |  | PASS
6 |  | To valiate Detractor, passive and promoters section |  |  |  | To check once with dev for all options working and also do we need to show colon or not* - fine
7 |  | To validate Key Performance indicator, Buddy Interaction and store visit graphs | [5 empty] | PASS
8 |  | To validate qudrant chart |  |  |  | All the four qudrant names should be displayed correctly on Qudrant Chart* | All four names quadrant names are overlying on each other which is incorrect | FAIL
9 |  | To validate employees faviourites word cloud | [5 empty] | PASS
10 |  | To validate Suggestions and Recommendations Word Cloud | [5 empty] | PASS
11 |  | To validate entry table
| 11.1 | To validate excel file download functionality |  |  |  | Suggestion -Confirm with dev - what comes in Negative Experiences should renamed as Suggestions |  | PASS
| 11.2 | To validate Search box functionality | [5 empty] | PASS
| 11.3 | To validate table entries formatting - Positive experience/Negative experience/ Someone to refer for Metro |  |  |  | Even the large text should be accomadataed withing the table margins* | Large text sentence are going out of the margin boundries | FAIL - Can be Quick fix
| 11.4 | To test the functionality of "Previous" button |  |  |  | It should redirect to the next page at left side* | In actual it's not redirecting to the next web page | FAIL - Can be Quick fix
| 11.5 | To test the functionality of "Next" button |  |  |  | It should redirect to the next page at right side* | In actual it's not redirecting to the next web page | FAIL - Can be Quick fix
8 | To validate automated emails sent to new joiner - email on 1st day and 3rd month email
9 | To validate email sent to line manager on 3rd month
Forms working modules
On submission this page comes up
Translated to english from urdu

## SurveyTool-Dashboard3rdMonth-LM (hidden)
Dashboard url -http://10.16.148.18/survey-tool-pakistan/pakistan/survey/dashboard
Testing in Chrome browser
3rd Month Line Manager Dashoboard functionality
TC ID | Sub-TC number | Name of the testcase | Description | Steps to be carried out | Testdata (if any) | Expected Results | Actual Results | Status | Tests Executed By | Execution date
1 |  | To validate Header part of Feedback Dashboard |  |  |  |  | Can be center aligned - confirm with dev
2 |  | To validate 3rd Month new joiner KPI dashboard
| 2.1 | To check the functionality of "3rd Month LM" button |  |  |  | It should show KPI data of 3rd Month Line Manager | It show as LM instaed of Line Manager - Confirm with dev | Fine for now discussed with dev
| 2.2 | To validate Date selection field
| 2.3 | To validate "Select Country" drop down box |  |  |  | It should show country options to select in drop down box | Country options are not shown in drop-down box |  | Post-live checks
| 2.4 | To validate "Select City" drop down box |  |  |  | It should show city options to select in drop down box | City options are not shown in drop-down box
| 2.5 | To validate "Select Company" drop down box |  |  |  | It should show company options to select in drop down box | Company options are not shown in drop-down box
| 2.6 | To validate "Select department unit" drop down box |  |  |  | It should show department options to select in drop down box | Department options are not shown in drop-down box
3 |  | To validate "Total no. of people filled the form"
| 3.1 | To validate the title formatting | [5 empty] | PASS
| 3.2 | To validate the count | [5 empty] | PASS
4 |  | To validate "Avarage overall onboarding experience"
| 4.1 | To validate the title formatting |  |  |  | As a suggestion- It can be - "Avearge no. of Overall Onboarding experience", also to ask about ":" should be shown after name or not* | In actual it is - "Average Overall Onboarding Experience" | To confirm with dev
| 4.2 | To validate the count |  |  |  | As a suggestion- It should be round off instaed of in decimal like 8/10 instaed of 8.25/10 - not an issue | In actaul it shows decimal point value - 8.25/10 | Confirmed
5 |  | To validate NPS section |  |  |  | To check once with dev for all options working |  | PASS
6 |  | To valiate Detractor, passive and promoters section |  |  |  | To check once with dev for all options working and also do we need to show colon or not
7 |  | To validate Key Performance indicator, Buddy Interaction and store visit graphs | [5 empty] | PASS
8 |  | To validate qudrant chart | [5 empty] | PASS
9 |  | To validate employees faviourites word cloud | [5 empty] | PASS
10 |  | To validate Suggestions and Recommendations Word Cloud | [5 empty] | PASS
11 |  | To validate entry table
| 11.1 | To validate excel file download functionality |  |  |  | Confirm with dev - what comes in Negative Experiences |  | PASS
| 11.2 | To validate Search box functionality | [5 empty] | PASS
| 11.3 | To validate table entries formatting - Positive experience/Negative experiences |  |  |  | Even the large text should be accomadataed withing the table margins* | Large text sentence are going out of the margin boundries | FAIL - Can be Quick fix
| 11.4 | To test the functionality of "Previous" button |  |  |  | It should redirect to the next page* | In actual it's not redirecting to the next web page | FAIL - Can be Quick fix
| 11.5 | To test the functionality of "Next" button |  |  |  | It should redirect to the next page* | In actual it's not redirecting to the next web page | FAIL - Can be Quick fix
8 | To validate automated emails sent to new joiner - email on 1st day and 3rd month email
9 | To validate email sent to line manager on 3rd month
Forms working modules
On submission this page comes up
Translated to english from urdu